CAPSTONE PROJECT REPORT

Report 2 - Project Management Plan

Pactkeeper - Tactical Strategy Role-Playing Game System

| Name | Student ID | Role |
| --- | --- | --- |
| Nguyễn Bách Hiệp | SE192114 | Team Leader |
| Lê Vũ Văn | SE190612 | Team Member |
| Lê Nguyễn Tuấn Khoa | SE194755 | Team Member |
| Võ Hoàng Thắng | SE182121 | Team Member |
| Lê Cao Khánh Hoàng | SE192527 | Team Member |

Supervisor: Phạm Thanh Trí

- Ho Chi Minh, September 2026 -

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	5

1.3 Project Risks	6

2. Management Approach	7

2.1 Project Process	7

2.2 Quality Management	7

2.3 Training Plan	8

3. Project Deliverables	8

4. Responsibility Assignments	9

5. Project Communications	10

6. Configuration Management	10

6.1 Document Management	10

6.2 Source Code Management	10

6.3 Tools & Infrastructures	11

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 21/09/2026 | A | Nguyễn Bách Hiệp | Initial draft of Report 2 - Project Management Plan |
| 25/09/2026 | M | Vo Hoang Thang | Checking and & Modify Project Deliverables, Responsibility Assignments, and Project Communications |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Authentication & Player Profile |  | 10 |
| 1.1 | Google OAuth / Steam ticket login, JWT session | Medium | 3 |
| 1.2 | Player profile (level, exp, gems) | Simple | 2 |
| 1.3 | Team formation / unit loadout config | Medium | 5 |
| 2 | PvP Matchmaking & Combat |  | 22 |
| 2.1 | Match queue, port allocation, reconnect | Medium | 6 |
| 2.2 | Timeline/instant server-authoritative combat engine | Complex | 10 |
| 2.3 | Match history & result reporting | Simple | 3 |
| 2.4 | Disconnect / timeout watchdogs | Simple | 3 |
| 3 | Story Mode & Tutorial System |  | 26 |
| 3.1 | Chapter/scene progression & backend tracking | Medium | 6 |
| 3.2 | PvE battle with guide vs. scripted AI opponent | Medium | 6 |
| 3.3 | Plot/guided-tutorial sequencer (text, guided click, triggers) | Complex | 10 |
| 3.4 | SFX / audio implementation for Story & tutorial | Simple | 4 |
| 4 | Gacha, Shop & Payment |  | 19 |
| 4.1 | Gacha banner, pull, duplicate compensation | Medium | 6 |
| 4.2 | Shop system (direct item purchase with gems) | Medium | 5 |
| 4.3 | PayOS top-up integration | Medium | 6 |
| 4.4 | Purchase order history | Simple | 2 |
| 5 | Reward & Action Log System |  | 8 |
| 5.1 | Action entity + Facts logging | Simple | 2 |
| 5.2 | RewardRule / RewardProgress evaluation engine | Complex | 6 |
| 6 | Admin & Moderation Dashboard |  | 15 |
| 6.1 | Content & balance management (gacha, shop, definitions) | Medium | 7 |
| 6.2 | Live-ops moderation (bans, session control, action logs) | Medium | 8 |
| 7 | Companion Web |  | 5 |
| 7.1 | Top-up / payment website (React) | Medium | 5 |
| 8 | Infrastructure & DevOps |  | 4 |
| 8.1 | VPS deployment, systemd service, firewall | Simple | 4 |
| 9 | Social & Competitive Systems (in development) |  | 14 |
| 9.1 | Friend system - add/remove/view friends, status (backend) | Medium | 6 |
| 9.2 | Ranking / leaderboard system | Medium | 8 |
| Total Estimated Effort (man-days) |  | 123/5 = 25 |  |

### 1.2 Project Objectives

The project aims to deliver a stable, server-authoritative online SRPG with a working PvP loop, a Story/tutorial onboarding path, and supporting meta-game systems (gacha, payment, rewards) by the end of the capstone period, together with an admin/moderation layer sufficient for live operation.

Quality

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | 100% of PRs | - | - | Peer review before merge to main branch |
| 2 | Unit Test | Core backend services | - | - | Reward evaluation, gacha rate rolls, combat step-cost math |
| 3 | Integration Test | API ↔ DB flows | - | - | Auth, matchmaking, gacha pull, payment webhook |
| 4 | System Test | Full match loop | - | - | Client + headless server + backend, end to end |
| 5 | Acceptance Test |  |  |  |  |

Milestone Timeliness (%): tracked per sprint against the schedule in Section 3; target ≥ 80% of sprint goals completed on time.

Allocated Effort (man-days): see the WBS in Section 1.1 (132 man-days total across 5 members).

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Third-party OAuth/payment integration failure (Google, Steam, PayOS) | High | Medium | Test each provider early in isolation; keep a fallback dev-login path; monitor provider status pages. |
| 2 | VPS/production deployment instability (build/runtime mismatch, firewall, port access) | High | Medium | Use self-contained publish builds; systemd auto-restart; keep the previous VPS alive as rollback during migration. |
| 3 | Combat desync between server-authoritative state and client prediction | High | Medium | Full state resync on reconnect; server is single source of truth; token-based decision validation. |
| 4 | Scope growth mid-project (e.g., reward/action-log system added after initial planning) | Medium | High | Explicitly scope new features to a minimal first pass; defer advanced variants (e.g., per-skill reward conditions, replay) to future work. |
| 5 | Uneven task distribution / single-member bottleneck on core systems | Medium | Medium | Weekly Zalo check-ins; team leader tracks blocking dependencies; document architecture so any member can pick up a module. |
| 6 | MongoDB schema drift between client-defined data (ScriptableObjects) and backend-defined data (DB definitions) | Medium | Medium | Single documented source of truth per data type; reconcile explicitly before writing SRS content that depends on it. |

## 2. Management Approach

### 2.1 Project Process

The team follows Scrum. Work is planned in sprints (approx. 1-2 weeks), each ending with a short review against the sprint goal and a retrospective adjustment for the next sprint. The team leader (Nguyen Bach Hiep) acts as de facto Scrum Master and Product Owner given the team's size, prioritizing the backlog against the current review milestone (Review 1 / 2 / 3) and the mentor's feedback.

Sprint cadence:

- Sprint Planning: backlog items pulled from the WBS (Section 1.1), prioritized by review-milestone dependency.

- Daily coordination: asynchronous status updates via Zalo, not a formal stand-up given the team's schedule.

- Sprint Review: working build demoed internally; blocking issues escalated to the mentor if unresolved.

- Sprint Retrospective: brief adjustment of task assignment or scope for the next sprint.

### 2.2 Quality Management

The team applies the following practices to reach the quality objectives in Section 1.2:

- Defect Prevention: shared architectural conventions (documented patterns for repositories/services/controllers on the backend; layer separation between data/UI/state-machine on the Unity client) so new code follows an established, reviewed shape rather than reintroducing the same class of bug.

- Reviewing: the team leader reviews pull requests into the main branch of each repository before merge, particularly for changes to shared/high-fan-out types (e.g., server match session, timeline manager).

- Unit Testing: targeted at deterministic, high-risk logic - reward rule evaluation, gacha probability rolls, combat step-cost calculations.

- Integration Testing: API-level tests against a MongoDB test database for authentication, matchmaking, gacha pulls, and payment webhook handling.

- System Testing: full manual playtests covering client + headless dedicated server + backend together, before each review milestone.

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Unity Netcode for GameObjects (server-authoritative multiplayer) | All members contributing to combat/matchmaking | Project start, self-paced (~1 week) | Waived if the member already has prior Netcode/multiplayer experience |
| ASP.NET Core + MongoDB backend patterns | Members working on backend controllers/services | Project start, self-paced (~1 week) | Waived if familiar with a comparable REST + document-DB stack |
| Git branching, commit hygiene, and repository migration workflow | All members | Ongoing; | Mandatory |
| Linux VPS operations (systemd, firewall, deployment) | Team leader | At first deployment; ongoing as needed | Mandatory for whoever owns deployment |

## 3. Project Deliverables

Internal technical milestones and external report deliverables. Report dates align with the three-review capstone schedule; passing Review 1 secures the project, with Reviews 2-3 used to raise the score.

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Repository setup - Backend and Unity Client repositories initialized | 14/09/2026 | Sprint 0 |
| 2 | Core gameplay loop - auth, loadout, PvP combat, matchmaking | 18/09/2026 | Sprint 0 |
| 3 | Story/tutorial system, gacha, payment integration functional | 21/09/2026 | Sprint 0 |
| 4 | Report 1 - Project Introduction | 21/09/2026 | Review 1 |
| 5 | Report 2 - Project Management Plan | 21/09/2026 | Review 1 |
| 6 | Reward & Action Log system implemented | ~05/10/2026 | Post Review 1 |
| 7 | Admin & Moderation dashboard functional | ~12/10/2026 | Post Review 1 |
| 8 | Friend & Ranking systems functional | ~19/10/2026 | Post Review 1 |
| 9 | Report 3 - Software Requirement Specification | TBD | Review 2 |
| 10 | Report 4 - Software Design Document | TBD | Review 2 |
| 11 | Report 5 - Test Documentation | TBD | Review 2 |
| 12 | Report 6 - Software User Guides | TBD | Review 3 |
| 13 | Report 7 - Final Project Report (merged) | TBD | Final grading |

## 4. Responsibility Assignments

D~Do; R~Review; S~Support; I~Informed; <blank>- Omitted

| Responsibility | Hiệp | Văn | Khoa | Thắng | Hoàng |
| --- | --- | --- | --- | --- | --- |
| Project Planning & Tracking | D | S | S | S | S |
| Gameplay design & core system architecture | D | S |  |  | S |
| Backend API baseline & database (ASP.NET Core + MongoDB) | D | S |  |  | S |
| Unity core systems (combat, timeline, matchmaking) | D | S | S |  | S |
| Story mode - baseline & system design | D |  | D |  |  |
| Story mode - tutorial fixes & polish | R | S | D |  |  |
| Gacha system (frontend + backend) | R | S |  |  | D |
| UI implementation & frontend-API integration | S | D |  |  | S |
| SFX / audio |  |  | D |  |  |
| Shop system | S |  |  |  | D |
| Top-up / payment system | S |  |  |  | D |
| Friend system (backend, in development) |  |  |  |  | D |
| Ranking system (in development) |  |  |  |  | D |
| Admin & moderation dashboard (frontend + backend) | R |  |  | D |  |
| VPS deployment & DevOps | D |  |  | S |  |
| Report 1 - Project Introduction | D | S | S | S | S |
| Report 2 - Project Management Plan | D | S | S | S | S |
| Report 3 - SRS (overall) | S | S | D | S | S |
| Report 3 - SRS (admin/moderation sections) | R |  |  | D |  |
| Diagramming (ERD, use case, architecture) | R | S | D | S | S |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Daily status update | All team members | Share progress, surface blockers | Daily, async | Zalo group chat, Discord |
| Sprint review & retrospective | All team members | Demo working build, adjust next sprint's plan | End of each sprint (~1-2 weeks) | Voice call (Zalo/Discord) |
| Mentor sync | Team leader + mentor | Report feedback, design decisions, review readiness | Every Tuesday | In person / chat |

## 6. Configuration Management

### 6.1 Document Management

Reports and diagrams are drafted collaboratively in Google Docs/Sheets and finalized as .docx files following the FPT University report templates. Each report keeps a Record of Changes table documenting date, change type (Added/Modified/Deleted), owner, and description, so revisions between review milestones are traceable. Diagrams (ERD, use case, architecture) are maintained in Miro/draw.io with shared, editable source files rather than static images only, so any member can update them as the system evolves.

### 6.2 Source Code Management

The project uses Git for the backend and (initially) Unity DevOps Version Control (Plastic SCM) for the Unity client, migrated to Git partway through the project. Five repositories are maintained:

- Backend — ASP.NET Core Web API + MongoDB

- Unity client / headless dedicated server

- Top-up / payment website (React)

- Admin dashboard — frontend (React)

- Moderator dashboard — frontend (React)

Each repository is committed independently by the member(s) who own that system, per the Responsibility Assignments in Section 4.

To keep the repository history clean and readable for grading, the team commits the codebase in logical, feature-grouped commits (e.g., models, repositories, services, controllers as separate commits) rather than a single bulk commit, so reviewers can follow how each system was built up.

- Branching: a single main branch per repository for the current project size; feature work is developed locally and merged after review.

- Commit convention: commits are scoped to one logical change or feature group at a time.

- Secrets: environment-specific configuration (connection strings, JWT secrets, payment keys) is excluded via .gitignore and never committed; production configuration is deployed directly to the VPS.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Unity 6.x (C#, Unity Netcode for GameObjects), ASP.NET Core 9 (C#), React + TypeScript (top-up website, admin dashboard, moderator dashboard) |
| Database | MongoDB (Atlas, cloud-hosted) |
| IDEs/Editors | Visual Studio Code, Unity Editor, Claude Code |
| Diagramming | Miro, draw.io (diagrams.net) |
| Documentation | Microsoft Office, Google Docs/Sheets |
| Version Control | Git / GitHub (backend, Unity client, top-up website, admin dashboard, moderator dashboard), Google Drive (documents) |
| Deployment Server | Linux VPS (Ubuntu 22.04) - self-contained ASP.NET Core publish, systemd-managed backend service, headless Unity dedicated server spawned per match |
| Third-party services | Google OAuth, Steamworks (test app ID), PayOS payment gateway |
| Project management | GitHub Issues/Projects (tasks), Zalo (team communication) |